## Slide 1: Timeline for Capstone Project - CKME 136
Building a statistical model to predict the energy efficiency for residential buildings Student Walter Cios / Stud. ID 500791945 |  |  |  | 
Project Initial Steps |  | Abstract Literature Review |  | 
Main Project Work & Initial Results |  |  | Initial Results Presentation | 
Final Results |  |  |  | Final Results & Project Report
Final Presentation |  |  |  | 
Fall 2017 |  |  |  | 
Sep 14 – Oct 02 | Oct 02 – Nov 02 | Nov 03 - Nov 20 | Nov 21 - 26 | Nov 27-30
Prepare Final Presentation
Working on Conclusions & Final report
Various Models Creation
Back to Status Summary
Models Selection and Evaluation
Final
Presentation
Reviewing Additional Models
Data Cleaning &
Preparation
Project Selection & Abstract
Literature review, data description and approach
Exploratory Data
Analysis
Define Model Evaluation
Procedure